# DEIS Three-Year Plan

Summary Framework

School Name:   Ringsend College

Roll Number: 70200D

Period of Plan: September 2024 – August 2027

Date of Ratification by Board of Management: TBC

Foundation of the DEIS Plan for Ringsend College

The staff and community of Ringsend College believe that a foundational component of a successful education is the positive relationships between staff and students.

The DEIS plan and all school policies have been developed with a goal of building a positive community in which every student feels supported, recognised and respected.

The goals and targets are set with the intention of helping students to achieve their potential. We aim to provide equality in the provision of educational opportunities through targeted supports.

DEIS Themes and Educational Priorities

DEIS Groups

| Retention and Attendance | D Scott (Group Leader), Julie (SCP), Patrick HSL, C Lambert, S Grier |
| --- | --- |
| Literacy and Numeracy | E Dooley (Group Leader), M Hughes, L Greenhalgh, C Lynch, P Hadrys, S Doyle |
| Examination Attainment and Supporting Educational Transitions | A McNally (Group Leader), A Kerrigan, F Flaherty, B Cleary, G Byrne, A Conway |
| Partnership with Parents and Partnership with Others | C McNeela (Group Leader), C Moran, E Kenny, Patrick HSL, D White |

| Summary Plan to promote RETENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Target(s): - To increase retention of students from 1st year to Junior Cert from baseline 83% by 1% each year. - To increase retention of senior cycle students from the start of 5th year to LC (LCE, LCVP and LCA) over each of the next 3 years by 1% each year. Baseline data from 23/24 is 94%. |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| Attendance Meetings to highlight students at risk of leaving school | 1,2 | HSCL, SCP, DP | DP | Monthly | VSware/attendance data |
| CARE Team Meetings to address any issues related to retention of students and support of minority groups. | 1,2 | P, DP, GC, SCP, HSCL, SEN | P | Weekly | n/a |
| Programmes – JCSP, TY, LCVP, LCA | 1,2 | JCSP Coordinator, TY Coordinator, LCVP teachers | Programme Coordinators | On-going | Coordination hours (voluntary), teaching hours |
| SCP Interventions – Attendance focus groups, 6 week interventions | 1,2 | SCP | SCP Coordinator | On-going, new cohort every 6 weeks | SCP team and funding. |
| Facilitation of Extra & Cross-Curricular Activities e.g., chess, green schools, etc. | 1,2 | All staff. | All staff | On-going | School funds |
| Student Council | 1,2 | A McNally | A McNally | Four times per year | n/a |
| Prefect Leadership Team | 1,2 | L Greenhalgh | L Greenhalgh | Six times per year | n/a |
| Counselling available for all students | 1,2 | Guidance Counsellor | Guidance Counsellor | On-going | n/a |
| Career Guidance counselling 1 on 1 | 1,2 | Guidance Counsellor | Guidance Counsellor | On-going | n/a |
| SCP Easter & Summer Camp for potential/incoming primary school students, secondary students assist in coordinating | 1,2 | HSCL/ SCP | HCSL/SCP | Easter/Summer holidays | SCP Funding |
| SCP 1 on 1 mentoring of targeted students | 1,2 | SCP | SCP | Weekly in 30 min/ 1 hour slots | SCP Funding |
| Provision of breakfast and hot lunches. | 1,2 | Fresh Today | P, DP | Daily | Dept. of Education funding |
| The Breakthrough project | 2 | P, C Moran, C McNeela | P | Monthly meetings | Breakthrough project |
| Monitoring and Evaluation: As with all DEIS schools, retention is at the forefront of our goals for our schools. For target 1, with our data we are evaluating at the end of each year what the rate of the cohort completing their Junior Cert in that year, how many of those students have we retained from first year. Data will be presented in percentage form with additional information relating to students who have left the school. The data for target 2 will be collated from the students completing the Leaving Certificate in the previous year and evaluating the level of retention from the start of 5th year. Data to be presented in percentage form and include additional qualitative data related to students who have left. - Retention rates will be calculated on a bi-annual basis and reviewed by the DEIS coordinator and attendance officer. - Personalised interventions will be put in place for all students at risk of not completing JC or LC by SCP in consultation with the DP. - Bi-annual review of actions to be completed by the DEIS team and any adjustments necessary |  |  |  |  |  |

| Summary Plan to promote ATTENDANCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Target(s): - Increase the percentage of SC student attendance (cohort A) from 75% to 77% by the end of year one, 79% by the end of year two and 81% by the end of year three across all year groups. - Increase the percentage of SC student attendance (cohort B) from 31% to 33% by the end of year one, 36% by the end of year two and 40% by the end of year three across all year groups. *Where cohort B is our identified group of students who are school reluctant and have interventions in place with SCP, HSL and the guidance counsellor and have attendance of less than 50%. Cohort A have attendance at greater than 50% |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| Regular communication between school, HSCL and parents. | 1, 2, | HSCL, Parents, GC | HSCL | Daily | Phone calls, letters |
| Attendance policy communicated to all students and parents | 1, 2 | DP | DP | Yearly in September, revisited in January during Tutor time | Part of journal |
| Term reports outline full and partial day absences | 1, 2 | Exam Coordinator | Exam Coordinator | 4 reports per student per year |  |
| Care Team Referrals | 1, 2, | Care Team | P & DP | Weekly on Monday |  |
| Attendance initiatives - positive attendance month, positive punctuality month. | 1, 2 | Tutors, HSCL D. Principal, SCP, JCSP Coordinator | DP | Twice a year | JCSP certificates and funding for prizes, DEIS funding for awards |
| Extra & Cross-Curricular Activities – Football, GAA, cookery, cross country, athletics, Green schools, chess club, athletics etc. | 1, 2, | P, DP, Teachers | P | Weekly, ongoing |  |
| SCP Attendance initiatives and small group mentoring | 1, 2 | SCP staff, HSCL | SCP Coordinator | Ongoing in 6 week interventions |  |
| Monitoring and Evaluation: Attendance will be monitored on a daily basis and monthly by DP, SCP and HSCL. When attendance issues occur, procedures laid out in Attendance policy to be implemented. Attendance statistics will be compiled by the DEIS coordinator Attendance group & Attendance officer at the end of each term to monitor progress using data gathered from VS Ware. Cohort A and B to be identified by previous year’s attendance data. Attendance data to be gathered from VSWare, looking at overall attendance for the year. Ongoing efforts made by school management to ensure VSWare data as accurate as possible. |  |  |  |  |  |

| Summary Plan to improve LITERACY LEVELS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase the number of 1st year students who read for pleasure from 42.4% when they start in Sept by 2% by the end of 1st year for each of the incoming 1st year groups over the three year period. - To increase the reading ages of students from the baseline of reading age of x to y in 1st years in each of the three years. *Accelerated reading programme being implemented this year, baseline data to be input when complete. |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| All JCSP students attend 3 English periods per week plus 1 library period | 1, 2 | JCSP Junior Cycle Classes | English teacher, JCSP Co-ordinator | Weekly | School library, Sora App, Books |
| Key words, definitions and terms are displayed in all classrooms. | 1,2 | All teachers | Subject teachers, JCSP Co-ordinator | Daily | Key word posters and copies, textbooks |
| Literacy Initiatives e.g. Drop Everything and Read, Focus on grammar, Examination term initiative. | 1, 2, | All classes | DP, teachers | On-going | Library, Sora App, Classroom resources |
| Literacy trips, events and workshops | 1,2, | JCSP Junior Cycle Classes | English teacher , external facilitators | Twice yearly | English teacher, theatre, cinema, local library |
| SNIP Programme for targeted SEN students | 1, 2 | SEN dept., teachers | SEN Coordinator | On-going | SNIP programme resources |
| SEN interventions for targeted students with CAT4 of 3 or less | 1, 2, | SEN dept., teachers | SEN Coordinator | Daily, ongoing | Standardised testing, learning materials |
| Teacher recommendations for targeted SEN students accessible on VSWare | 1, 2, | SEN dept., teachers | SEN Coordinator | Daily, ongoing |  |
| Teachers display which book they are currently reading on their door. | 1, 2 | Teachers | DEIS Coordinator | On-going |  |
| Monitoring and Evaluation: Data collected from 1st years using surveys, small group interviews, feedback from library class teachers and Accelerated Reading Testing. Students will be monitored in 1st year for the targets but the initiatives in place will benefit the whole school. The school recognizes the links between literacy levels and future success and aims to aid our students to meet their potential in this regard. |  |  |  |  |  |

| Summary Plan to improve NUMERACY LEVELS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase the number of 1st and 2nd year students who can accurately calculate percentages by 2% by the end of year 1, 2% by the end of year 2 and a further 1% by the end of year 3. (Baseline 48% in 1st year and 57% in 2nd year) - To increase the number of 1st and 2nd year students who can accurately read an analogue clock by 2% by the end of year 1, 2% by the end of year 2 and a further 1% by the end of year 3. Baseline currently at 68%. - To decrease the number of LC students taking Foundation level maths by 2% by the end of year 1, 1% by the end of year 2 and a further 1% by the end of year 3. Number of students who took FL in 2024 was 35%. |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| Streaming from 3rd Year on where possible | 3 | P, DP | P, DP | Ongoing |  |
| Maths Noticeboard, maths week, maths initiatives. | 1, 2, 3 | Maths dept. | Maths dept. | Ongoing | Noticeboards, posters |
| Inclusion and highlighting of numeracy based tasks in classes, e.g. weighing and measuring, problem solving, measuring, estimations, interpreting of graphs and data, use of technology etc. | 1, 2, 3 | All teachers, DP | DP | Ongoing | Linked in Schemes of Work |
| Financial Literacy initiative for all students, introduced November 2024 - Grant pending | 1, 3 | E Dooley | DEIS Coordinator | Ongoing | Grant |
| SEN support and interventions for targeted students | 1, 2, 3 | SEN dept. | SEN Coordinator | Daily | Testing and learning materials. |
| Maths grinds available to all students | 1, 3 | DP, HSCL, GC | DP, HSCL, GC | Weekly | Educational organistaions, private funding |
| Introduction of team-teaching in selected maths classes | 1, 3 | SEN dept. | SEN Coordinator | Ongoing |  |
| Teachers to encourage students to read the analogue clock in class, all class clocks to have added signage to aid students. | 1,2 | All teachers |  | Ongoing | Class resources |
| Teachers return all exams with fraction score, students to convert to percentage. | 1, 3 | All teachers | All teachers | Ongoing | Class tests |
| Monitoring and Evaluation: - To be done using questionnaires sent to all 1st and 2nd year students, which questions featuring analogue clocks. - In class tests with percentage calculation questions in Sept, Jan, May - Exam data to be analysed post Leaving Cert exams. |  |  |  |  |  |

| Summary Plan to improve EXAMINATION ATTAINMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase the number of students taking HL core subjects at JC by 2% in year 1, another 2% in year 2 and a further 2% in year 3% from baseline 13% in 2024 (0% in Gaeilge, 28% in English, 12% in Maths) - To increase percentage of students taking HL subjects at SC by 2% in year 1, another 2% in year 2 and a further 2% in year 3% from baseline 20% in 2024 |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| SEN interventions for targeted students (based on STEN/ CAT4) | 1,2, | SEN dept. | SEN Coordinator | Ongoing | SIPs, Cat4 data |
| Teachers share and co-create success criteria with students so that they can assess their own learning through self-assessment and peer assessment, and identify areas for improvement and strategies to achieve improvement. (LAOS 2022, p. 31) | 1,2, | All teachers | DP | Ongoing | Teachers classroom resources |
| Teachers collectively agree and implement whole-school approaches to learning and teaching that include the use of online platforms and other digital technologies to improve students’ experiences and outcomes (LAOS 2022, p. 33) | 1,2, | All teachers | P | Ongoing | Classroom resources |
| Teachers model enthusiasm and enjoyment in learning, and thereby create a learning environment where students are self-motivated to engage in, extend and enjoy their learning. (LAOS 2022, p. 30) | 1,2, | All teachers | P | Ongoing | Work of the week posters, school social media |
| Highlight the correlation between good attendance and exam success to both students and parents. | 1,2, | All teachers, Attendance Officer, DP, P | DP | Ongoing. Attendance | VSware, attendance initiatives |
| Work with Higher Education Institutions (Trinity College, BRIDGE 21, Access, UCD, TUD link school) that will expand the learning opportunities for students. | 1,2, | All teachers, GC | Guidance Counsellor | Ongoing | Meeting and planning time |
| Assess and apply for reasonable accommodations in state examinations | 1, 2 | GC, Exam Coordinator | Exam Coordinator | Yearly | Educational assessment tools |
| JCSP Initiatives to support students at Junior Cycle | 1 | All teachers, JCSP Coordinator | JCSP Coordinator | Ongoing | Planning and evaluation time, JCSP funding |
| Supervised Study | 1,2 | Supervising teachers, DP | D. Principal | Weekly (3 days) from January* | Classroom, attendance sheets. |
| Study Skills Workshop for 5th, 6th years and 3rd years | 1, 2 | GC, DP | GC, DP | Annually |  |
| Analysis of RACE testing | 1, 2 | 3rd and 6th year students | SEN Coordinator, Guidance Counsellor | Yearly, October, November | Testing materials |
| Intentional design of homework to maximise learning. | 1,2 | All teachers | DEIS Coordinator | Ongoing | Homework policy in journal, homework discussed at staff meetings |
| Opportunities for grinds and school supplies through bursaries such as SVP, St Andrews | 1,2 | GC | GC | Ongoing |  |
| Inclusion of constructive comments on term reports and teacher training in relation to same. | 1, 2 | All teachers, DP | Exam Coordinator | Four times per year |  |
| Student self-reflection during tutor time at the beginning and end of each term on their learning goals, challenges, achievements | 1, 2 | All tutors, DP | DEIS Coordinator | Four times per year |  |
| Inclusion of LC points on all Senior Cycle term reports | 2 | Exam Coordinator | Exam Coordinator | Two times per year |  |
| Monitoring and Evaluation: Data will be analysed from results of Junior Cert and Leaving Cert examinations when the results become available. Data will be accessed throughout the year using the tracker to identify students who are not achieving their potential. Classroom performance and results from class test to identify students for streaming and opportunities such as grinds. |  |  |  |  |  |

| Summary Plan to Support Educational Transitions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase the percentage of students offered opportunities to progress to further education (CAO, PLC and apprenticeships) from 74% (22% CAO, 39% PLC, 13% apprenticeship) by 1% each year. - To increase the percentage of 1st year students who report feeling settled and happy after the first three months of secondary school by 2% each year for three years (2024 first years 37% report feeling settled, 52.6% report they are still adjusting). |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| SCP Easter and Summer Camp | 2 | Incoming 1st year students | SCP Coordinator, HSCL Officer | Yearly, Easter, Summer |  |
| Maths and Cookery Activities | 2 | Potential 1st year students from feeder primary schools | HCSL Officer, Maths and Home Economics teacher | Yearly, Jan/Feb |  |
| Prefect mentoring of 1st year students | 2 | L Greenhalgh, Prefects | L Greenhalgh | Yearly Sept - Dec |  |
| 1st Year students begin a day early, participate in ice-breaker activities | 2 | P, DP, Tutors | P, DP | September |  |
| TY Parents - Senior Cycle Options | 1 | GC, Programmes Coordinator | GC | Annually - May |  |
| SCP Team Building programme (6 week) for 1st years | 2 | SCP | SCP Coordinator | Yearly Sept-Oct |  |
| Whole-school sports day and mixed-year activities | 2 | P, DP, Tutors, teachers | P, DP | Ongoing, termly |  |
| Carry out Aptitude and Interest testing in TY in Guidance class. Discuss career implications with students individually. | 1 | Guidance | Guidance Counsellor, TY Coordinator | Jan – May |  |
| Timetabled Guidance classes for TY, 5th and 6th year | 1 | Guidance Counsellor | Guidance Counsellor | Ongoing |  |
| Study skills/interview skills | 1 | Guidance Counsellor | Guidance Counsellor | Annually, Sept to May |  |
| CAT4 General Ability assessments for incoming students to support Teaching & Learning |  | GC | GC | Annually | Educational assessment tools |
| Invite speakers from 3rd Level and FE colleges to speak to students and students attend HEI open days. | 1 | Guidance Counsellor | Guidance Counsellor | Weekly /monthly |  |
| Meet all 6th year students to encourage them to apply to CAO, HEAR, TAP, PLCs and apprenticeships. Give information about grants and scholarships. | 1 | Guidance Counsellor | Guidance Counsellor | Throughout the year |  |
| Student participation on Bridge to College events, Freirium, Lir Theatre workshops etc. | 1 | Programmes Coordinator | Programmes Coordinator | Yearly |  |
| Parents information evening and HEAR DARE workshop for all parents | 1 | Guidance Counsellor, DP | Guidance Counsellor | Yearly, September, November | Information booklets |
| Primary School Principals networking | 1 | P, SEN Coordinator & HSCL | P | March/May |  |
| Monitoring and Evaluation: For target 1, data will be collected using surveys with first years in Sept, at Christmas and before the summer and feedback from GC. Data from target 2 will collected after the Leaving Cert results by Guidance Counsellor contacting students directly. |  |  |  |  |  |

| Summary Plan to promote PARTNERSHIP WITH PARENTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase PA membership by 50% in year 1, 33% in year 2 and 25% in year 3. Currently two parents in PA. - To increase attendance at PTM by 5% in year 1, 2% in year 2, 2% in year 3. Working from an educated estimate of 50% attendance. |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| Open Day | 1, 2, | P, DP, teachers | P | Yearly, October | School, Advertising |
| LCVP Christmas Event | 1, 2, | LCVP teacher and students | LCVP Teacher | Yearly, December | School, local community support |
| Work with local youth services when necessary (Café, Clubs) | 1, 2 | SCP Coordinator | SCP Coordinator | Ongoing |  |
| Home Visits | 1, 2 | HSCL | HSCL & P | Ongoing |  |
| Parent Representative Group (participate in NCCS Senior Cycle Review, discuss new school tracksuits, participate in cookery classes, assist at school events, child protection, contribute to policy review) | 1, 2 | P, DP, HSCL | DP | 4 meetings annually |  |
| Give advance notice of Parent teacher meetings, in journal, by text, on social media, send letter/text to thank parents for attending | 1, 2 | All students, parents, teachers | DP | 3 meetings annually |  |
| Senior Cycle Parents Information evening for 6th years and LCA | 1, 2 | GC | GC | Annually |  |
| Increased use of social media to engage parents | 1, 2, | DP, B Cleary | DP | Ongoing |  |
| Coffee Morning - PA | 1, 2 | PA | PA | 1st Term |  |
| 1st Year Parent Coffee Morning | 1, 2 | P, DP | P, DP | 1st Term |  |
| Guidance Initiatives (Supporting parents with digital literacy skills - PEDL) | 1, 2 | GC | GC | Annually Feb |  |
| Email class lists for better communication with parents | 1, 2 | DEIS | DEIS | Sept-Dec |  |
| Parent Teacher Football Match | 1, 2, | HSCL | HSCL | Yearly in May |  |
| Monitoring and Evaluation: Data to be collected at events to monitor parent engagement and attendance. Sign in sheets at PTM’s. DEIS coordinator to liaise with HSCL. |  |  |  |  |  |

| Summary Plan to promote PARTNERSHIP WITH OTHERS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Targets: - To increase uptake by students in opportunities from outside organisations in TY from baseline 30%, by 2% in each of the next three years. - To increase opportunities for students in each year group to engage with organisations from outside the school by 1% each year. 76 opportunities last year in total. |  |  |  |  |  |
| Actions: |  |  |  |  |  |
| Measure | To address target(s) no. | Who? | Lead responsibility | When? | Resources? |
| Shared document for parents of TY students to show the opportunities available to students. | 1, 2 | All teachers | Programme Coordinator | Ongoing |  |
| BOM invited to school events | 1, 2 | P | P | Ongoing |  |
| School Christmas Event | 1, 2 | All Teachers | LCA Teachers | September-December | School, local community support |
| Coffee Morning for Irish Hospice Foundation | 1, 2 | Programme Coordinator | Programme Coordinator | Yearly, September | School, Local community support |
| Teachers invite speakers from outside agencies to facilitate workshops, e.g. Shoutout, Aware, Dublin RCC, Bank of Ireland etc. | 1, 2 | Teachers, P | P | Ongoing |  |
| Invite Primary school students in during the day for events | 1, 2 | LCA students, Voc Prep teacher | LCA Voc Prep teacher | Yearly | School |
| Careers Night with Corporates and FE/HE Institutions | 1, 2 | P, DP, GC | GC | Yearly | Corporates |
| BITC CICSO workshops | 1, 2 | LCVP Coordinator, A McNally | LCVP Coordinator | Ongoing |  |
| TUD Partnership and 'Link School' for Junior and Senior Cycle students. | 1, 2 | Guidance Counsellor | Guidance Counsellor | Annually; October |  |
| TY and 5th year work experience | 1, 2 | TY Coordinator, LCVP teacher | TY Coordinator, LCVP teacher | Twice yearly in TY, once in 5th year |  |
| Trinity School of Distinction Initiatives for Junior and Senior Cycle | 1, 2 | GC, C Moran | GC | Ongoing |  |
| Promotion of school on Social Media | 1, 2 | B Cleary | B Cleary | Ongoing, daily |  |
| Community involvement TY | 1, 2 | Programmes Coordinator | Programmes Coordinator | Two one week blocks |  |
| The Breakthrough Project - 5th and 6th Year | 1, 2 | P, C Moran, C McNeela, A Kerrigan | C McNeela | Ongoing | Breakthrough project funding |
| Monitoring and Evaluation: Opportunities for student and engagement with outside organisations to be keep track of using TY shared document and school calendar. All teacher to include activities in both the calendar and data to be updated to central file which will reference each year group. Data to be analysed at the end of the year to determine both opportunities and level of engagement. |  |  |  |  |  |

It is possible that a measure may address a number of targets